## login-page
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Login functionality — verifying valid/invalid login, redirect to home, and new user registration link.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify that only registered users can login, unregistered users are rejected, and login redirects to Home dashboard.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Page Load & Navigation
1 | Open http://localhost:3000 in browser |  | Login page should load as the first/default page | Login page loaded — Register and Login options visible |  | Pass
2 | Verify no other page is accessible without login (type /home in URL) |  | Should redirect to /login automatically | Redirected to /login as expected |  | Pass
Valid Login
3 | Enter a registered email and correct password |  | Fields accept input without errors | As Expected |  | Pass
4 | Click "Sign In" button |  | User should be logged in and redirected to /home | Redirected to Home dashboard with 3 cards |  | Pass
5 | Verify Home dashboard shows 3 cards: Questions, Materials, Profile |  | All 3 cards visible and clickable | As Expected |  | Pass
Invalid Login
6 | Enter unregistered email and any password, click Sign In |  | Error: "No account found with this email" | Error message displayed correctly |  | Pass
7 | Enter registered email but wrong password, click Sign In |  | Error: "Incorrect password" | Error message displayed correctly |  | Pass
8 | Leave email blank and click Sign In |  | Form validation prevents submission | Browser validation triggered |  | Pass
9 | Leave password blank and click Sign In |  | Form validation prevents submission | Browser validation triggered |  | Pass
New User Navigation
10 | Click "Create an account" link on login page |  | Should redirect to /register page | Redirected to Register page as expected |  | Pass

## register-page
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Registration functionality — verifying new user creation, validation, duplicate check, and DB storage.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify that new users can register, data is saved to MongoDB, and user is redirected to login after success.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Page Load
1 | Click "Create an account" from Login page |  | Register page should open | As Expected |  | Pass
2 | Verify all fields visible: Full Name, Email, Password, Confirm Password |  | All 4 fields and Create Account button present | As Expected |  | Pass
Valid Registration
3 | Enter valid Full Name, Email, Password (min 6 chars), matching Confirm Password |  | All fields accept input | As Expected |  | Pass
4 | Click "Create Account" button |  | Success message shown: "Account created successfully! Redirecting to login..." | Success message appeared |  | Pass
5 | Wait 2 seconds after success message |  | Auto-redirect to /login page | Redirected to login as expected |  | Pass
6 | Verify user exists in MongoDB Atlas (users collection) |  | User document saved with hashed password | User found in DB — password is bcrypt hashed |  | Pass
Validation Checks
7 | Leave Full Name empty and click Create Account |  | Error: "Please enter your full name" | Validation error shown |  | Pass
8 | Enter password with less than 6 characters |  | Error: "Password must be at least 6 characters" | Validation error shown |  | Pass
9 | Enter different values in Password and Confirm Password |  | Error: "Passwords do not match" | Validation error shown |  | Pass
10 | Register with already existing email |  | Error: "An account with this email already exists" | Duplicate email rejected |  | Pass
Navigation
11 | Click "Sign in" link at bottom of Register page |  | Redirected back to /login | As Expected |  | Pass

## questions
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Questions functionality — posting, browsing, searching, filtering, viewing and voting on questions.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify logged-in users can post questions, browse all questions, search/filter, view details and vote.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Browse All Questions
1 | Login and click "Questions" card on Home dashboard |  | Questions list page loads with all questions | As Expected |  | Pass
2 | Verify question cards show: title, body preview, tags, author, votes, views, status |  | All fields visible on each card | As Expected |  | Pass
3 | Verify questions from ALL users are visible (not just own) |  | Questions from multiple users displayed | As Expected |  | Pass
Search & Filter
4 | Type a keyword in the search bar and press Enter |  | Questions matching keyword in title/body are shown | Search results filtered correctly |  | Pass
5 | Type a tag name in filter tag input and press Enter |  | Only questions with that tag are shown | Tag filter working correctly |  | Pass
6 | Click Clear button to reset filters |  | All questions shown again | As Expected |  | Pass
7 | Search for a term that matches no questions |  | Empty state shown: "No questions found" | Empty state message displayed |  | Pass
Ask a Question
8 | Click "+ Ask Question" button |  | Redirected to /ask page | As Expected |  | Pass
9 | Fill Title, Body, Tags and click Post Question |  | Question created and user redirected to question detail page | As Expected |  | Pass
10 | Submit question without Title |  | Validation error shown | Browser validation triggered |  | Pass
11 | Submit question without Body |  | Validation error shown | Browser validation triggered |  | Pass
12 | Verify newly posted question appears in questions list |  | Question visible in list with correct data | As Expected |  | Pass
Voting
13 | Click ▲ vote button on a question |  | Vote count increases by 1 | As Expected |  | Pass
14 | Click ▲ vote button again on same question (toggle) |  | Vote count decreases by 1 (un-vote) | As Expected |  | Pass
15 | Verify same user cannot vote twice on same question |  | Second vote toggles instead of adding | As Expected |  | Pass

## answers
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Answers functionality — posting answers, voting, accepting best answer, and view count.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify any logged-in user can answer any question, vote on answers, and question author can accept best answer.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
View Question & Answers
1 | Click on any question in the questions list |  | Question detail page loads with full title, body, tags, author | As Expected |  | Pass
2 | Verify view count increments on each visit |  | View count increases by 1 per visit | As Expected |  | Pass
3 | Verify answers from all users are displayed sorted by accepted first, then votes |  | Accepted answer at top, rest sorted by votes | As Expected |  | Pass
Post an Answer
4 | Scroll to "Write Your Answer" section and type an answer |  | Textarea accepts input, character count shown | As Expected |  | Pass
5 | Click "Post Answer" button with valid text |  | Answer appears in answers list immediately without page reload | As Expected |  | Pass
6 | Try clicking Post Answer with empty textarea |  | Error: "Please write an answer before submitting" | Validation error shown |  | Pass
7 | Verify answer shows author name and date |  | Author name and date visible on answer card | As Expected |  | Pass
8 | Verify a different user can also answer the same question |  | Multiple answers from different users displayed | As Expected |  | Pass
Vote on Answers
9 | Click ▲ vote on an answer |  | Vote count increases by 1 | As Expected |  | Pass
10 | Click ▲ vote again on same answer (toggle off) |  | Vote count decreases by 1 | As Expected |  | Pass
Accept Answer
11 | Login as question author and view own question with answers |  | "✓ Accept" button visible next to each non-accepted answer | Accept button visible only to question author |  | Pass
12 | Click "✓ Accept" on an answer |  | Answer marked as Accepted — green border and "✅ Accepted Answer" banner appear | As Expected |  | Pass
13 | Verify question status changes to "✅ Solved" |  | isSolved flag set to true, shown in questions list | As Expected |  | Pass
14 | Login as different user and verify Accept button NOT visible |  | Accept button hidden for non-authors | As Expected |  | Pass
15 | Click Back to All Questions button |  | Returns to /questions-list page | As Expected |  | Pass

## materials
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Study materials functionality — uploading, browsing, searching, and downloading files.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify users can upload study materials, files are stored on server, and others can search and download.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Upload Material
1 | Click "Materials" in the navbar |  | Materials page loads with upload form and materials list | As Expected |  | Pass
2 | Fill Title, Subject, Tags, Description and select a PDF file |  | All fields accept input, file selected | As Expected |  | Pass
3 | Click "⬆ Upload" button |  | Material uploaded successfully, appears in materials list below | As Expected |  | Pass
4 | Try uploading without selecting a file |  | Browser validation prevents submission | As Expected |  | Pass
5 | Try uploading without entering Title |  | Validation error shown | As Expected |  | Pass
6 | Try uploading an unsupported file type (e.g. .exe) |  | Upload rejected — only PDF/DOC/PPT/IMG allowed | Upload rejected with error |  | Pass
7 | Verify uploaded file shows uploader name on card |  | Uploader name visible on material card | As Expected |  | Pass
Browse & Search
8 | Verify materials from all users are visible |  | All shared materials displayed in grid | As Expected |  | Pass
9 | Type keyword in search bar and press Enter |  | Materials matching title/description shown | As Expected |  | Pass
10 | Search for non-existent material |  | Empty grid shown | As Expected |  | Pass
Download
11 | Click "⬇ Download" link on a material card |  | File downloads or opens in new tab | File opened in new tab as expected |  | Pass

## profile
Test Case Project |  | P2P Tutoring Platform | Test Case Description | User profile page — viewing account info, personal stats, own questions, and logout.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify the profile page shows correct user info, stats, and personal question history.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Profile Page
1 | Click "Profile" card on Home or Profile in navbar |  | Profile page loads with user details | As Expected |  | Pass
2 | Verify avatar shows first letter of user name |  | Initials shown in colored circle | As Expected |  | Pass
3 | Verify name and email are displayed correctly |  | Correct name and email shown from JWT token | As Expected |  | Pass
4 | Verify 3 stat cards show: Questions Asked, Solved, Reputation |  | All 3 stat cards present with correct values | As Expected |  | Pass
5 | Verify "My Questions" section shows only questions asked by this user |  | Only current user questions listed | As Expected |  | Pass
6 | Click on a question in My Questions list |  | Navigates to question detail page | As Expected |  | Pass
7 | Verify solved questions show ✅ Solved badge |  | Solved badge visible on accepted questions | As Expected |  | Pass
Logout
8 | Click "⎋ Logout" button on Profile page |  | User logged out, JWT removed from localStorage | As Expected |  | Pass
9 | Verify redirect to /login after logout |  | Login page shown after logout | As Expected |  | Pass
10 | Try accessing /home after logout by typing in URL |  | Redirected back to /login (ProtectedRoute) | As Expected |  | Pass
11 | Verify Logout also works from Navbar Logout button |  | Same behavior — redirected to /login | As Expected |  | Pass

## auth-security
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Authentication and security testing — JWT tokens, bcrypt hashing, protected routes, and session management.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify all security mechanisms work: token validation, password hashing, route protection, and unauthorized access prevention.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
JWT Token Tests
1 | Login and check localStorage in browser DevTools → Application tab |  | user object with _id, name, email, token stored | Token found in localStorage |  | Pass
2 | Clear localStorage manually and try to access /home |  | Redirected to /login (no valid token) | As Expected |  | Pass
3 | Modify the token in localStorage to an invalid value and refresh |  | API returns 401, user redirected to login | As Expected |  | Pass
Password Security
4 | Register a user and check MongoDB Atlas users collection |  | Password stored as bcrypt hash (starts with $2b$) | Password is hashed — never stored as plain text |  | Pass
5 | Register same email twice |  | Second registration rejected with duplicate email error | As Expected |  | Pass
Route Protection
6 | Without logging in, navigate to /ask |  | Redirected to /login | As Expected |  | Pass
7 | Without logging in, navigate to /materials |  | Redirected to /login | As Expected |  | Pass
8 | Without logging in, navigate to /profile |  | Redirected to /login | As Expected |  | Pass
9 | Without logging in, navigate to /questions-list |  | Redirected to /login | As Expected |  | Pass
10 | After login, navigate to /login directly |  | Redirected to /home (PublicRoute protection) | As Expected |  | Pass

## api-testing
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Backend REST API endpoint testing — verifying correct responses, status codes, and error handling.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Test all API endpoints directly to ensure correct behavior, status codes, and data returned.
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Auth APIs
1 | POST /api/auth/register with valid data |  | HTTP 201 — { message: "Account created successfully" } | HTTP 201 returned |  | Pass
2 | POST /api/auth/register with duplicate email |  | HTTP 400 — { message: "An account with this email already exists" } | HTTP 400 returned |  | Pass
3 | POST /api/auth/login with valid credentials |  | HTTP 200 — { _id, name, email, token } | JWT token returned |  | Pass
4 | POST /api/auth/login with wrong password |  | HTTP 401 — { message: "Incorrect password" } | HTTP 401 returned |  | Pass
5 | GET /api/auth/profile with valid Bearer token |  | HTTP 200 — user object without password | As Expected |  | Pass
6 | GET /api/auth/profile without token |  | HTTP 401 — { message: "Not authorized" } | HTTP 401 returned |  | Pass
Questions APIs
7 | GET /api/questions |  | HTTP 200 — { questions[], total, pages } | Paginated response returned |  | Pass
8 | GET /api/questions?search=python |  | HTTP 200 — filtered questions matching search term | Search filtering works |  | Pass
9 | POST /api/questions with Bearer token |  | HTTP 201 — new question object with author populated | As Expected |  | Pass
10 | POST /api/questions without Bearer token |  | HTTP 401 — Not authorized | HTTP 401 returned |  | Pass
11 | PUT /api/questions/:id/vote with Bearer token |  | HTTP 200 — { votes, voted } | Vote toggled correctly |  | Pass
12 | DELETE /api/questions/:id as question author |  | HTTP 200 — { message: "Deleted" } | Question deleted |  | Pass
13 | DELETE /api/questions/:id as different user |  | HTTP 403 — Not authorized | HTTP 403 returned |  | Pass
Answers APIs
14 | GET /api/answers/:questionId |  | HTTP 200 — answers array sorted by accepted, votes | As Expected |  | Pass
15 | POST /api/answers/:questionId with Bearer token |  | HTTP 201 — new answer with author | As Expected |  | Pass
16 | PUT /api/answers/:id/accept as question author |  | HTTP 200 — { message: "Answer accepted!" } | As Expected |  | Pass
17 | PUT /api/answers/:id/accept as different user |  | HTTP 403 — Only question author can accept | HTTP 403 returned |  | Pass
Materials APIs
18 | GET /api/materials |  | HTTP 200 — materials array | As Expected |  | Pass
19 | POST /api/materials with file and Bearer token |  | HTTP 201 — material with fileUrl | File saved in uploads/ |  | Pass
20 | POST /api/materials without file |  | HTTP 400 — { message: "No file uploaded" } | HTTP 400 returned |  | Pass

## deployment-testing
Test Case Project |  | P2P Tutoring Platform | Test Case Description | Deployment verification — testing the live deployed site on Vercel + Render + MongoDB Atlas.
Created By |  |  | Reviewed By |  | Version |  | 1.0
QA Tester's Log |  | Test cases verified against deployed P2P Tutoring Platform
Tester's Name |  |  | Date Tested | 2026-05-10 | Test Case (Pass/Fail/Not Executed) |  | Pass
Test Scenario | Verify the entire platform works correctly on the production deployment (live URLs).
Step # | Step Details |  | Expected Results | Actual Results |  | Pass / Fail / Not executed / Suspended
Frontend (Vercel)
1 | Open https://tutoring-platform.vercel.app in browser |  | Login page loads as first page | As Expected |  | Pass
2 | Verify page loads without errors in browser console |  | No console errors | As Expected |  | Pass
3 | Verify site works on mobile browser |  | Responsive layout on mobile screen | As Expected |  | Pass
4 | Refresh page on /questions-list (SPA routing test) |  | Page loads correctly (vercel.json rewrites working) | As Expected |  | Pass
Backend (Render)
5 | Open https://p2p-tutoring-backend.onrender.com |  | JSON response: { message: "✅ P2P Tutoring API Running" } | API running confirmation shown |  | Pass
6 | Register new user on live site |  | Account created — user saved in Atlas | As Expected |  | Pass
7 | Login with registered user on live site |  | JWT token received, redirected to Home | As Expected |  | Pass
8 | Post a question on live site |  | Question saved in Atlas and visible in list | As Expected |  | Pass
9 | Note: First request after inactivity may take 30 seconds |  | Render free tier cold start expected behavior | Cold start observed — works after 30s |  | Pass
Database (MongoDB Atlas)
10 | Login to Atlas and open p2p_tutoring database |  | Collections: users, questions, answers, materials visible | All 4 collections present |  | Pass
11 | Verify user documents have hashed passwords |  | password field starts with $2b$ (bcrypt hash) | As Expected |  | Pass
12 | Verify question documents have author as ObjectId reference |  | author field is ObjectId pointing to users collection | As Expected |  | Pass